## Slide 1
entra21 Program
Phase I: Results, Lessons Learned and Sustainability Paths
Presented by:
Susan Pezzullo of the International Youth Foundation
Elena Heredero of the Multilateral Investment Fund

## Slide 2
Findings: Targeting Youth
Successful targeting:
19,649 youth served
54/46 gender split
77% w/ secondary degree; 17% working at baseline
Most youth from poor households
Outreach through multiple vehicles, careful selection:
Executing Agencies used combination of written application, tests and interviews
Screened for criteria, motivation and ability
Successfully controlled attrition:
87% completed training cycle, 13% dropped out

## Slide 3
Findings: the 32 Executing Agencies
Mixed origins
Degrees of closeness to private sector
Array of core competencies
Only a handful “did it alone”
Critical success factors:
  Ability to identify good partners
  Job placement services was area of least competence when projects began
  Leadership, ability to learn from mistakes, and respond

## Slide 4
Findings: Assessing Labor Market and Delivering Training
Most common methods for gauging market used: surveying business people, accessing existing market information, and using internships to evaluate relevance of curriculum
Had to abandon or add content, where training was not aligned to employer needs
Wide range of hours and overall duration: 1300 highest to 270 lowest
General breakdown of hours: 46% technical, 28-30% internship, 24-26% life & other skills

## Slide 5
Findings: Job Placement Services
Dual approach: Satisfy youth and employers
Need designated coordinator with entrepreneurial approach
Created sense of team with training providers
Under-estimated the amount of time invested in JPS
Lack of openings most commonly cited by youth as impediment

## Slide 6
Findings: Employment Rates and Quality
54% employment rate (average); range 82%-14%
Most work was permanent (58%)
Most contracts were formal (78%)
Most youth received benefits (76%)
Using minimum wage as point of reference: 74% made MW or better; 21% made 150% of MW
50% of working youth report wages not sufficient to cover expenses even if earning minimum wage or better
However 82% of youth satisfied with jobs because they are interesting

## Slide 7
Findings: Use of Time and Who Benefited
At baseline, 62% not in school or working
By follow up, only 25% not in school or working
However…..
Participation in civic or other organizations dropped; and
Not all youth benefitted equally (females had lower odds of being employed and males earned on average 32% more)

## Slide 8
Findings: Sustainability of Services Offered to Youth
Three main strategies:
  Diversification of funding post-entra
  Transfer of practices
  Institutionalization
Less probability of continuity: Diversification of funding
Promising examples
  Transfer of practices: Argentina, Colombia
  Institutionalization: Panama, Chile
Non promising cases

## Slide 9
Thank you!
Susan Pezzullo (IYF): spezzullo@IYFNet.org
Elena Heredero (MIF): elenah@iadb.org