## Slide 1: Large Scale Contracting out of Basic Health Services For the Poor in Guatemala The SIAS Program Design, Processes and Results
IDB-IBRD Joint Conference on the
Political Economy of Service Delivery
Jerry La Forgia
June 2, 2005
Notes: Supported by two IDB loans. I was the project leader for the implementation of the first loan.

## Slide 2: Overview
SIAS Program (1997-2001)
  Rationale
  Objectives
  Design
  Performance
  Issues and Problems
  Political Economy of Change
Notes: Results (impact, coverage, production, costs) – based on HH survey, provider cost survey, and analysis of contracting processes.
The overall objective of the research is three-fold: (i) assess processes and procedures related to the contracting of NGOs and extending immunization services through the NGO-based delivery system, (ii) assess the impact of the Program on coverage of basic health services by comparing key indicators in communities served by the NGOs with to those obtained in communities served by the MSPAS (using a household survey), and (iii) determine the relative economic efficiency of NGO and MSPAS providers in delivering basic health services.
.

## Slide 3: Guatemala: Health Situation (circa 1996)
11million: 50% indigenous
IMR 46/1000 nationally;
Indigenous population
  Mostly rural
  64/1000 IMR (vs. 44 for non-indigenous)
  Maternal Mortality: 300-500/100,000
  Prevalence of ARI/diarrhea 40-50%
  17% births attended trained professional or midwife (vs. 55% for non-indigenous)
  Distance, cost and cultural barriers
  Low utilization rates
Notes: Mayan speaking
Situation is bad, but much worse for mayan populations who generally live in the rural and mountainous north and northwestern section, but migrate to the coast for agricultural work once or twice a year.
Highest infant mortality and maternal mortality rates in the region

## Slide 4: Coverage Extension Program
Focus on rural and indigenous populations
Basic package (24 services/activities)
Two delivery platforms (Direct and Mixed)
Outreach model (direct and mixed models)
  Assigned geographical areas (jurisdictions)
  Community centers (outposts)
  MD, auxiliary nurse, rural health technician (monthly visits)
  Promoter volunteers, midwives (community-based)
Agreements (convenios)
Notes: This and next few slides aim to establish the context of the CEP
Conceptualized in 1996-97, launched in late 1997: Driven by Peace Accords signed in 1996 and in that same year a new government came to power -- Pease accords called for significant improvements in health – reducing by half infant and maternal mortality by 2000
Extend to rural, indigenous populations
Service package of 24 services and activities grouped in four areas: maternal care, infant-child care, attention to illness, and environmental health
Direct and mixed providers assigned to areas that MOH providers did not reach; assigned geographical areas of between 8, 000 and 12,000 populations expected to establish community based outposts where most services and activities were delivered: outreach team consisted of MS, nurse auxiliary, rural health technician which visited the outposts monthly, also worked with and trained promoter volunteer5s and midwives at the community level. Also was place for distribution of essential drugs
Traditional –expect to provide coverage to entire catchment area but not enter into new geographical areas – not an out reach programs
Health post suppose to deliver same package but in catchment areas;
Start from scratch: created agreements known as convenios – had to set legal and regulatory framework for contracting out. This was done through the new health law in early 1998. In fact, the approval of the law enabled the rapid expansion starting in 1998.

## Slide 5
Notes: Direct, Mixed and traditional
Community centers for Direct and Mixed
Health posts for traditional
Direct: received per capita and responsible for all purchasing (except vaccines) service delivery, reporting and financial management. As will see later, assigned most distant areas.
Mixed: also received a per- capita. But were Responsible for contracting some personnel – mainly MDs, and for all purchasing (except vaccines) -- but MSPAS assigned other personnel. Supported MOH personnel who were responsible for service delivery, but only financial reporting. Generally assigned areas closer to MOH health centers where – according to MOH – there should be health posts.

## Slide 6: Agreements/NGOs by Year
Notes: This slide shows the rapid expansion of
1997-1998 –big jump in agreements under implementation; reached 136 agreements with 88 NGOs – established bout 1800 CCs, and claimed coverage extension of 3 million. The new health law cleared the path for contracting.
2/3s Direct and 1/3 indirect
Also claimed to meet vaccination coverage targets

## Slide 7: Nominal Population Coverage
Notes: Nominal coverage of about 3 million people

## Slide 8: Comparison of Performance, 2001
Service/Activity | Target | Trad. | Mixed* | Direct
% prenatal care | 80 | 75 | 87 | 78
Ave. # prenatal visits | 3 | 2.9 | 3.0 | 2.8
% tetanus coverage pregnant women | 95 | 62 | 64 | 55
% children < 5 with:* BCG DPT 3 Polio 3 Measles | 95 95 95 95 | 93 80 81 82 | 93 89 90 90 | 88 81 82 82
% children <2 with diarrhea who rec’d ORT | 100 | 42 | 52 | 46
Infant growth monitoring (% children <2 during previous 3 months) | 90 | 3 | 8 | 12
* Quiché and Verapaz
Notes: Targets were global national targets, but included in the norms annexed to the agreement.
At least 2 prenatal care visit
Avg no. of PNC visits for those with at least one visit
Odds ratio: mixed model were significantly different from traditional providers on nearly all services; direct model showed no significance difference from traditional providers except for growth monitoring – but must recall that direct providers were assigned to distant communities in which starting conditions were probably much worse. Under these conditions they were having similar impact and performance as traditional providers located in areas closer to cities and towns.
Note that we do not have a baseline – and therefore do not know the answer to a KEY questions: which communities showed the greatest improvement. It is possible that the baselines for the direct communities were much worse than for the other two groups, but our study cannot pick this up.
Without a baseline—difficult to determine progress---anectodal evidence suggests that vaccination coverage was less than 30% and prenatal care about 25%

## Slide 9
Average monthly production and productivity by
output category And provider type, 2001
Notes: In terms of production in terms of all services (ALL) and the Basic Package (PBS) PSSs demonstrate markedly higher production and productivity than the HPs and slightly but still significantly higher higher than the mixed model providers. The differences hold even if we control for vaccinations.Not shown, if we only included providers with physicians, again the differences hold.

## Slide 10
Average Per Provider Costs:
Observed and Adjusted, 2001 (in Q$)
Notes: Average per/provider costs are significantly higher for direct and mixed provides. Even after adjusting for volunteer labor, are about 1/3 of PSS costs and ½ of mixed costs.

## Slide 11
 p = <0.05 (differences between each pair of providers for both nominal and effective coverage).
Cost per Capita by Provider Type,
Nominal and Effective Population Coverage,
(adjusted costs)
Notes: However, if we look at the per capita cost of effective coverage, direct providers are the better deal.
Effective coverage was drawn from the HH survey and based on the observed demand for prioirty interverntions (ARI care, diarrhea care, prenatal care and well-baby checkups).
Effective pop. Coverage:52 % for PSS, 25 for ADMSS and 26 for PSs.
In conclusion, the available evidence at least based on first 4-5 years suggests a fairly successful innovation. The new direct and mixed provider models performed as well, and in the case of mixed providers, often better than traditional health care services in deliverying a basck health package to rural, indigenous communities that previously had no, or limited access to health care services.These models were generally more productive and displayed higher labor productivity than the traditional model. But they also have significantly higher unit costs—but display lower per capita costs when accounting for effective population coverage. These models are viable alternatives as long as government continues t commit the additional funding required to underwrite the higher costs.

## Slide 12: Issues and Problems
Catchment areas-- not a level playing field
Open contract model
Weak contracting infrastructure
  In-flight adjustments
  Payment delays
Few (if any) providers delivered the full package
Financial sustainability
Notes:   Mixed --- closer to roads and towns
  Direct --- distant communities
  Traditional --- health posts already located close to roads and towns
    No coverage extension
Open contract: Took anyone that met minimal standards – some not really qualified– led to some problems later on
MSPAS proceeded to expand with a fledgling contracting structure: though they did good job from the beginning regarding financial management of the contracts – in part due to fear of corruption – technical monitoring was often ad hoc, especially during the early years; this contributed to some contractors providing less than full package.
But delays in issuing payments and shifting MOH priorities also contributed to delivery of less than full package (vaccines) as well as low and unadjusted per capita payments; MoH gave different signals regarding service priorities – one year –1998 – vaccination – many NGOs reported stopping other services during a few months to meet vaccine coverage objectives.
Financial sustainability depended on external financing. Always unclear whether future governments would draw from national resources to support the program.

## Slide 13: Political Economy of Innovative Program Design and Implementation
Used NGOs instead of expanding of MoH delivery network
Mixed model – not contemplated in original design
Assigning of catchment areas to Mixed and Direct providers
Legal framework
  High risk but necessary step
Incremental expansion rejected
  Expanded too quickly?
Notes: El MSPAS decidió usar ONGs para extender cobertua (modelos ASS e PSS) en lugar de expandir la capacidade de provisión del MSPAS. En outras palabras, el MPSAS hizo bypass de sua propria rede (para la extensión de cobertura). Esto fue la primera vez en sua historia del MSPAS que intentó usar terceiros para proveer servicios de salud. En parte , el MSPAS reconoció que el aparato publico del MSPAS (administración direta) no era suficientemente agil, flexible o robusto para a rápida extensión a grande escala. Qual fue el analisis politico de las ventajas e desventajas de hacer bypass de la rede de provisión del MSPAS e orientar SIAS a ONGs? Por que no considerabam usar el sector privado lucrativo?
El modelo de ASS no fue originalmente contemplado ni por el Projeto BID o por el MSPAS. Este modelo "tipo mixto" salió a base de discussiones políticas internas entre as autoridades del MSPAS e trabajadores de salud, particularmente os jefes de areas e los técnicos rurales, los cuales oponian el uso de ONGs. Seria interessante comentar sobre las debates politicos que resultaron en el "parto" del modelo ASS.
A decisión de colocar los PSSs en comunidades distantes e los ASSs en comunidades mas cerca a pequenas ciudades respondia también a las pressiones de los trabajadores del MSPAS quem estaban por vincularse a los ASSs. Estos trabajadores querian trabajar en comunidades que conocían y a su vez quedaron mas cerca de las pequeñas ciudades donde vivían. En cambio, a situación de acceso fue mas deficil y el estado de salud de la población era mas precaria que en las comunidades (distantes) asignadas a los PSS. Esta situación contribuia a que los ASS demostraban mejor desempeño que los PSS en la evaluación. Seria importante comentar sobre las pressiones de parte de los trabajadores de MSPAS sobre a assignación de comunidades a las ASSs e PSSs.
El nuevo codigo de salude hizo posible la existencia de SIAS y la contratación de ONGs mediande los "convenios. También el código fue desafiado jurídicamente. El MSPAS salió exitoso tanto con el codigo como con el desafio juridico. Seria interesante comentar sobre las "inversiones politicas" por parte del MSPAS para que el codigo saliera de Congreso sin modificaciones mayores, e que el desafio juurídico saliera a favor del MSPAS.
Incremental expansion – why not step into extension rather than doing everything at once. What drove this decision, especially given the absence of experience in contracting out health services.