## Slide 1
1
Public Private Partnerships (PPP)
in Portugal
Pedro Eiras Antunes
EIB – European Investment Bank
IADB, 8-9 December 2005
SPECIFIC ISSUES ABOUT THE SCUT PROGRAMME

## Slide 2
Autoestradas SCUT:
Interior Norte
Norte Litoral
Grande Porto
Beira Litoral-Alta
Costa da Prata
Beira Interior
Algarve

## Slide 3
SCUT projects – 100% delivered by 2007
Scut Beira Interior
176
176
Scut Interior Norte
156
87
69
Scut do Algarve
130
130
Scut Costa de Prata
104
92
12
Scut Grande Porto
64
15
49
Scut Beiras Lit./Alta
167
38
129
Scut Norte Litoral
113
70
43
TOTAL
910
608
302
Construction
Evaluation
Negotiation
2002
2003
1999
2000
2007
2008
2001
Built
(km)
Concession
Total
In
construction
1998
2004
2005
2006
Source: EP – Estradas de Portugal
Publicity
Contract awarding
(km)
(km)

## Slide 4
Strengths
Consistent tendering and evaluation structure.
It allowed development and availability of further 910 kms of motorway network on a shadow toll basis, complementary to additional real toll motorway, built/under construction and in pipeline of 442 kms and 197km, respectively.
Substantial improvement of level of service to end-users.
Positive impact on public administration (improved focus on performance).
Two-stage tendering process.
Strong adherence of banking community.
Weaknesses
Affordability: substantial budgetary impact – will it be sustainable?
Delays and cost overruns, mainly due environmental licensing problems.
Sub-optimal risk sharing is an issue.
Competitiveness in the tendering process maybe insufficient.
Contract management shortcomings.
Affordability concerns – high forecast financial burden to the state over next 20-yrs.
SCUT Programme Lessons

## Slide 5: SCUT Programme TC versus EP
No proper VFM/PSC analysis.
Too much weight on financial cost minimisation criteria (i.e. NPV of tolls) detrimental to other equally important quality criteria.
Competitiveness and comparability of proposals negatively impacted by poor quality evaluation criteria.
Sub-optimal risk sharing, e.g. environmental and traffic (banding / widening).
Sub-optimised financial costs.
Inadequate monitoring management capacity.
Implementation of PRN programme compromised by SCUT budgetary burden.
Positive effects from accelerated availability of roads, otherwise out of the scope of the state’s physical and budetary implementation capacity, not considered.
Environmental impact: EIS for corridors in most recent SCUTs approved up-front.
Despite of the problems identified by the TC, the state considers the adopted procurement model fundamentally robust.
Follow up: the need to strengthening the monitoring capability is recognised.
The SCUT concessions exclude construction of competing roads, but not the modernisation of existing ones.
TC – Court of Auditors
EP – Road Authority

## Slide 6: SCUT Programme Envisaged solutions
Improve the procurement process, e.g. risk sharing and incentive payments mechanisms.
Improve procedures for justification of PPPs, including better evaluation of environmental impacts and level of affordability supported by PSC.
Specialised PPP unit at the Ministry of Finance.
Improve information and transparency of the tendering processes.
Up-front licensing (inc. environmental) before tender.
Induce more innovation in contract design and adopt a more oriented output based approach.

## Slide 7: SCUT programme Post-script
Shadow toll payments will reach c. EUR 700m from 2007 (or 0.5% of GDP) for over 20-yrs, severely restricting budgetary flexibility to carry out other priority road investments foreseen in the national road programme.

## Slide 8
2007-2023 will be difficult years!
SCUT programme Is it affordable?

## Slide 9
SCUT Programme Shall some of the concessions converted to real toll?
Consumer Purchase Index of the municipalities crossed by several SCUT
(national average = 100)
Real tolled
Shadow tolled
Source: PT Gov.

## Slide 10
SCUT programme Post-script
Currently, EUR 500m of confirmed financial rebalancing awarded to various projects and potential for further up to c. EUR 1bn of claims, mainly due to environmental licensing and expropriation delays and unilateral changes in project design by the state. This compares to EUR 4.8bn of project costs foreseen at contract awarding.
The government appears open to renegotiate some of the concessions over the medium term to allow conversion to real tolling. This would entail additional investments which, together with likely worsening traffic risk profile would give rise to financial rebalancing claims from affected promoters. The selection criteria still needs to be clarified.

## Slide 11: SCUT programme Post-script
CONVERTING TO REAL TOLLS
  ARGUMENTS AGAINST
    The project contracts did not originally contemplate such possibility
    Not possible in all concessions
    Additional investment needs (significant investments in toll booths would arise)
    Technical difficulties for the collection of tolls
    Risk profile has been accepted and is contractually valid
COMPENSATION MEASURES (critical to achieve agreement on fin. reb. claims)
  Refinancing
  Extension of concession period
  Changes to scope of concession

## Slide 12: REFINANCING – AN OPTION?
Issues
  Reduce burden of SCUT payments
  Debt pricing adjustment to risk – can it be improved?
  Additional leveraging / term
  Meeting market expectations
  Improve IRR/ROE
Significant opportunities will arise in the future
Options
  New bank syndicate with different conditions
  Securitisation (wrapped bond issue)
  EIB loan with monoline
  Other

## Slide 13
REFINANCING – AN OPTION?
Challenges
  Tax treatment (withholding tax)
  Rating requirements
  Constraints under Portuguese law
  Subordinated debt
  Dealing with monolines
  Convincing the grantor
  Managing the security package
  Contract renegotiation and legal due diligence
AGREEMENT ON SHARING OF REFINANCING GAINS WITH THE GRANTOR!

## Slide 14: MAIN lessons from the SCUT programme
Challenges ahead:
  Improving the procurement
  Improving the contractual models
  Improving project selection and appraisal
  Reduce bidding costs
  Reduce financing costs and diversify funding
  Prepare for LT management of PPP relationships

## Slide 15
In general terms, the concessionaire has the right to request replacement of the financial balance of the concession under the following circumstances:
  Unilateral change of obligations imposed by the grantor or the conditions to perform the concession resulting in a substantial increase in costs or reduction in revenues
  Force majeure (war, hostilities, invasion, subversion, tumults, rebellion, terrorism, epidemics, atomic radiation, fire, lightning, severe floods, cyclones, earthquakes and other natural cataclysms)
  Change in law in ways that can result in substantial increase in costs or reduction in revenues (excluding general changes in tax, social security, labour and environmental law).
Usually, the financial rebalancing is calibrated, with regard to the base case audited financial model, to ensure that certain minimum ratios are maintained, including usually inter alia ADSCR, LLCR and IRR/ROE.
The financial rebalancing may be achieved through one or several of the following measures:
  Change in tariffs
  Direct compensation to the concessionaire
  Extension of the concession term
  Other mutually agreed solutions
FINANCIAL REBALANCING PROVISIONS IN PORTUGUESE PPPs

## Slide 16
http://www.eib.org