## Slide 1: Regional Projects- Role, Results and Challenges for Supervision
Kingston, Jamaica
May 3, 2007

## Slide 2: What makes a project regional?
Topics relevant for regional integration – (public sector, public goods)
Transfer of knowledge or technologies – leader and “adopting” countries
New concepts, similar approaches in all countries (homogenous cultures). Looking for similar or different results.
New concepts, different approaches in each country (heterogenous cultures). Looking for similar or different results.
Small size of individual countries or projects not eligible for funding under delegation of authority.

## Slide 3: It all depends on what the objectives are, and if you have a solid executing agency.

## Slide 4: Supra-national entities
Executive body
Ministerial representation
Counterpart funding
Political interference in contracting
Revolving door of political support
Political/technical dichotomy

## Slide 5: Organizational structures Supra-national Entities

## Slide 6: Supranational entities
Caribbean Agriculture Research and Development Institute Caribbean Centre for Development Administration
Caribbean Environmental Health Institute
Caribbean Development Bank
Caribbean Food Corporation
Caribbean Food and Nutrition Institute
Caribbean Regional Organization for Standards and Quality
Caribbean Regional Fisheries Mechanism
Caribbean Regional Negotiating Machinery

## Slide 7: Operational structure –one agreement, central administration
Single agreement, single purpose operation, complete harmonization.
Examples of results in Central America: Civil Aviation Safety Agency (ACSA- Ministries of Transportation, COCESNA flyover charges), OACI audits and FAA categorization, improved legislation and operations supervision, information systems, harmonized manuals and procedures Central American Monetary Council (CMCA –Central Banks, debt management, payment systems)treaty for payment systems, harmonization of standards and procedures for payments, improvements in national payment systems, systemic risk reduction

## Slide 8: Operational structure –one agreement, Central Administration
Centralized procurement and funds management. Lower administrative costs. Less jealousy as entity pre-exists as regional.
Consultants, long or short term, serve all countries, or selected countries/topics –minimizes contradictions in advice.
Group training sessions rotate among participating countries
Bank deals directly with central agency.

## Slide 9: Operational structure –one agreement, central administration
Supervision structure
  Similar to national project
  COF reviews procurement and disbursements
  COF attends regional meetings in country
  Utilize experts for mid term and final evaluations
  Read technical consultant reports –insist on executive summaries of salient points. Request occasional technical briefings.
  Semester progress reports with briefings on all countries

## Slide 10: Operational structure-one agreement with the Bank, decentralized administration

## Slide 11: Operational structure one agreement
One technical cooperation agreement with lead agency and collaboration agreements (subagreements) between lead and sub-agencies
  Advantages – Bank deals directly with lead implementing entity, regional considerations are managed by that entity. Simpler for procurement and financial management –for the Bank. Reasonable for ex –post supervision of procurement and disbursement at lead agency, reduce paperflow.
  Counterpart funding subdivided among participating countries

## Slide 12: Operation structure-one agreement, decentralized administration
Considerations
  Potential reduced ownership on the part of sub-implementing entities
  Perception of reduced status without a direct agreement with the Bank, possibly greater emphasis on central administration country (more money, more consultants of that nationality)
  Counterpart funding subdivided among participating countries, more difficult to account for, frequently as attributions rather than funds in a separate bank account. Burden for lead agency.

## Slide 13: Operation structure-one agreement and sub agreements, decentralized administration
Considerations:
  Single revolving fund from the Bank, requires sub-funds to sub-agencies – significant delays in justification and replenishment. LMS isn´t structured as yet for decentralized administration (one revolving fund per agreement-ATN)
  International funds transfers from lead agency to sub-agency in small amounts increase costs (depends on regional banking opportunities)

## Slide 14: Operational structure-one agreement and sub agreements, decentralized administration
  Requieres additional administrative support usually at sub-agencies, depending on initial capacity. Usually MIF project funds significantly increase the budget of the entity, and can overwhelm their installed capacity, which they realize only after they have signed the project. (hubris)

## Slide 15: Operation structure-one agreement and subagreements, decentralized administration
  Behaviors -Slow to initiate implementation, due to a double layer of learning curve with new hires at both levels, project management training possibly less effective, little supervision experience at lead agency. Larger budget than usual for them.
  Contact sub-agencies/Bank infrequent.
  Requires sufficient budget for lead agency to travel to sites and hold group training and technical sessions. Skype and e-mail help but are not sufficient

## Slide 16: Results
Successful results – Rainforest Alliance and sustainable tourism. Create and test training tools in different cultures, access fragile areas and vulnerable groups, enable technical and professional interchange with the international marketplace to sell the concept and build credibility.

## Slide 17: Results
Not so successful results – 50/50 partnership for outsourcing of design, supervision and evaluation. Lack of guaranteed cofinancing led to buy-in to other donor projects, reducing focus, influence, compliance and extending both the commitment and implementation periods. Executing institution – (University) chosen did not have installed capacity nor mandate for a grant-making agency. COF involvement in design and supervision greater than envisioned.

## Slide 18: Options for supervision

## Slide 19: Options for supervision
COF with lead agency reviews all procurement ex -ante or ex –post (ultimately responsible)
COF with lead agency carries out technical inspection visits, (big projects, remote areas, cost considerations)
COF in country carries out inspection visit on request, with specific TOR and visit report. Depends on relationships between specialists, workload and technical areas of interest.

## Slide 20: Options for supervision
  Concentrate on lead agency administration and use baseline study, mid term and final evaluations to cover all countries in technical areas. Have periodic project coordination meetings programmed held in country with lead agency, and attend. Annual audits, including all subagreements. (cost)

## Slide 21: Operational structure- multiple agreements

## Slide 22: Operational structure- multiple agreements
Central agreement with lead agency to cover regional aspects
Separate TC with each country

## Slide 23: Operation structure-separate agreements
Considerations
  Depends on size of national portion, and type of support (ta, training, matching grants)
  Allows for different project execution pace in countries, and dropouts
  Administrative structure in each country
  Crossed conditionality, scheduling and shared costs for regional aspects, potential delays
  Lead agency depends on goodwill, doesn´t control finances of national projects

## Slide 24: Operation structure-separate agreements
  One MPPMR for all agreements and implementing agencies
  LMS doesn´t accumulate counterpart correctly in its present application, (by TC not by ATN) skewing information on MPPMR

## Slide 25: Supervision
Similar to national project, requieres coordination among national projects and regional core
Requires coordination among COFs for MPPMR, baseline and evaluations for economies of scale and/or single consulting contract

## Slide 26: Coordination among COF
Different Representatives and corporate culture
Different management styles
Different approach with implementing agencies and procurement
Different perceptions and classification of MPPMR
Different MIF vs. Sector Specialist

## Slide 27: Project management and team building
Form
Storm
Norm
Perform
Evaluate and disband
IDB/MIF interventions –clear objectives reached with the implementing agency, coherent components, initial indicators and roadmap, have them hire a solid project manager, provide them with tools and training to minimize the sense of being overwhelmed with information.

## Slide 28: Tools
Workplan – annotated schedule of activities broken into contracting actions, identifying sequential or simultaneous actions. Have them analyze and re-think the GANTT in the design documents.
Draft TORs, and provide training in selection criteria and processes. Pull out the relevant sections of GS-2350-7 and GS-2349-7. Lesson learned - People can read, but they usually don´t.
Model contracts for individuals, consulting firms and services
Arrival of PROMIS for procurement, LMS 2 for disbursements and SISCOR 3 for electronic correspondence will either simplify or complicate MIF projects, depending on rigidities and workflow requirements.

## Slide 29: Tools
Check on their policies and procedures on travel and per diem, purchasing and contracting consultants.
Check on their cost center accounting capability
Use electronic documents and correspondence, make sure they have adequate software applications and connectivity with an organizational server or site for official correspondence.

## Slide 30: Tools
Semester reports -agree on a simplified format for overall project and for sub-projects –that gets to the point of the indicators from the logical framework, and can make PPMR easier.
Disbursement requests – agree with the financial specialist and the lead agency on the format for information from sub-projects and level of supporting documentation (may change with outsourcing of financial functions). Go expost wherever possible.

## Slide 31: Tools
Web based project management tools
Moodle.com, example http://eporfin.ecologicfinance.org enabling organization and document sharing among partners in different countries; M&E systems for following indicators, training information systems to track MiSMEs or individuals.
System for Contract product and payment monitoring (user friendly in Access)
Most Bank tools are to fulfill Bank needs for fiduciary controls, executing units also need simple implementation tools that don’t require expanded administrative services.

## Slide 32: It is possible. Thank you
Betsy Murray
betsym@iadb.org