## Slide 1: Steps for leading MIF projects Technical Cooperations
Elena Heredero
elenah@iadb.org
Multilateral Investment Fund
Inter-American Development Bank
Subregional meeting with MIF Specialists and Country Officers
Kingston, Jamaica
May, 2007

## Slide 3: Abstract phase
A. General information collected during the identification mission or based on the client’s proposal:
Preparation of the abstract: use the abstract template
Complete 1st part of institutional assessment
Project Registry – intranet OPUS: to obtain TC Number
  Client information/executing entity: name of legal representative, address and telephone number, email
  Project team: MIF/OPS, MIF/DEU, Legal, region, MIF/CO
  Totals
  Name of project in both languages

## Slide 4: Abstract Phase
4
B. POC:
Abstract and 1st part of institutional assessment to be sent to MIF’s Deputy Manager through IDBDOCS
To be scheduled in the POC (Fridays generally)
To be presented before the POC
POC emits Memorandum of Eligibility with recommendations for the design – a week after it has been presented

## Slide 5: CESI
5
Emailed to CESI: cesinet@iadb.org For consideration of this Committee.
To be scheduled on Mondays for discussion on Fridays.
Members of CESI send comments for which the Team Leader must respond to through email.
Said comments appear in CESI minutes, which requests for document to be resent or no action in particular.

## Slide 6: Progamming Committee
6
  To be sent through the intranet for consideration of the Programming Committee of the Bank: Project abstract and eligibility memorandum.
  Comments are recieved rarely.
  Office of the secretary makes sure that this Committee has given its approval, at the time it is being scheduled for the Donors Committee.
  - Publication

## Slide 7: Project Analysis
7
  Preparation of Donors Memorandum drafts and/or logical framework.
  Analysis mission: memorandums are sent to Country Director and Bank Representative reporting on the mission.
  During the mission: preparation of logical framework and budget, and initial preparation of operating regulations. Revision and agreement on execution mechanism. Institutional evaluation.
  Subsequent: finalization of Donors’ Memorandum, Annex 1: Logical Framework, Annex 2: Budget, Annex 3: List of related projects, when it is part of a cluster, Annex 4: Acquisitions plan, Annex 5: Operational Regulations.

## Slide 8: CRG
8
  Donors Memorandum and Division’s Chief Memorandum to be sent inviting to CRG: Members - Region Deputy Managers and corresponding division chiefs.
  To be sent for translation: Office of the Secretary – intranet. It is recommended that these translations be sent after the CRG to save $, unless on time restraint by due date.
  To be sent to CESI if requested, with memo where recommendations where noted.
  Virtual CRG – 5 working days, or physical –meeting for discussion.
  If virtual: Collection of recommendations and answers through email/telehone for discussion.
  Final negotiation with Client: Vo. Bo.
  Preparation of new version of documents highlighted for the translators follow up, or sent for the 1st time, if ok with time.

## Slide 9: VI. EVP- Office of the Vice President
9
  Donors’ Memorandum to be sent – CRG version and marked version with suggested changes and anexes:
  - Logical framework and budget: clean and marked
  - List of projects is included if it is a project cluster.
  - Resolutions of legal in both languages.
  - Non objection from country.
  - Remission on paper with: Manager’s Memorandum to executive VP with concurrence (Vo.Bo) from Chief of OPS noting the discussed aspects, copy of minutes of CRG, and memorandum from Team Leader to the Secretary, to be subsequently sent to Donors, noting the date of revision and approval from the CESI.
  2. Comments are expected in a week.

## Slide 10: VII. Sent to Donor’s Committee
10
  If there were no comments in EVP, Office of the secratary is in charge of sending to Donor’s Committee.
  It is necessary to coordinate dates with Chief Unit of Operations MIF.
  1. Presentation before Donors for final approval, if total is greater than US$500,000. If not, it is directed to short procedure: it is approved if there are no comments, 15 days after it is sent.
  2. Be assured that the project and annexs, are in IDBDOCS.

## Slide 11: VIII. Review Legal Agreement
11
  Ask lawyer for a draft of the legal agreement.
  Review and send to client.
  Prepare final version for signature.